## Dashboard
OOSH — AlmaLinux Platform Support
Project: | OOSH — Object Oriented Shell
Period: | 2026-02-22 to 2026-04-13 (~7 weeks)
Authors: | Hannes Nortje, Marcel Donges
Key Metrics
250+ | 7 | 25+ |  | 362/363* | 5/5
Commits | Weeks | Files Modified |  | Tests Passing | Platforms Pass
Total work volume | Feb 22 – Apr 13 | Across OOSH core |  | AlmaLinux 9 | Must-pass gate
Effort Breakdown
| Core AlmaLinux |  | Cross-Platform |  | Total
Commits | 161+ |  | 91+ |  | 250+
Focus Areas | 8 |  | 10 |  | 18
Total Repo |  |  |  |  | 800
AlmaLinux 9 is a must-pass gate for production. No code reaches prod without passing AlmaLinux tests.
* 1 intentional meta-test failure on AlmaLinux 9: a test that verifies failure detection itself — expected behaviour, not a regression.

## Timeline
Weekly Timeline — AlmaLinux Work (Feb 22 – Apr 13, 2026)
Week | Dates | Focus Area | Key Deliverables | Commits
1 | Feb 22 – Mar 1 | Foundation | odocker wrapper created, dnf/yum support, which → command -v, SSH ControlMaster fixes | 82
2 | Mar 1 – 8 | Platform Setup | AlmaLinux Docker image, platform matrix defined, RHEL install fixes, moreutils removed | 70
3 | Mar 8 – 15 | Release Pipeline | promote script + state machine, automated platform tests, v1.0.0 released, sparse array fix | 132
4 | Mar 15 – 22 | macOS + Portability | macOS CI pipeline, login shell/.bashrc fixes, portable sed -i, test suite hardening | 177
5 | Mar 22 – 29 | Multi-User Install | sudo PATH fix, UPG handling, auto-create user, cross-user install, .bash_profile portability | 196
6 | Mar 29 – Apr 5 | Docker & SSH | Docker socket access, shared SSH config + deploy key, POSIX BRE regex fix, notests param, git config | 130
7 | Apr 5 – 13 | Stabilisation | Report preparation, minor framework improvements | 13
TOTAL |  |  |  | 800

## Summary
OOSH — AlmaLinux Platform Support
Project: |  | OOSH — Object Oriented Shell
Period: |  | 2026-02-22 – 2026-04-13 (~7 weeks)
Authors: |  | Hannes Nortje, Marcel Donges
Total Commits: |  | 250+
Work Area | Category | Commits | Files Changed | Period | Status
Package Manager (dnf/yum) | Core | 1 | 5 | Feb 2026 | Complete
POSIX Compatibility | Core | 5 | 14 | Feb–Apr 2026 | Complete
Docker Infrastructure (odocker) | Core | 68 | 3+ | Feb–Apr 2026 | Complete
AlmaLinux Docker Image | Core | 1 | 1 | Mar 2026 | Complete
Installation Fixes (ossh install) | Core | 4 | 6 | Mar 2026 | Complete
User Management (RHEL) | Core | 1 | 1 | Mar 2026 | Complete
Platform Test Infrastructure | Core | 61 | 10+ | Mar–Apr 2026 | Complete
Release Pipeline | Core | 20+ | 10+ | Mar 2026 | Complete
Portable Shell (sed -i) | Cross-platform | 1 | 2 | Mar 2026 | Complete
Login Shell / .bashrc Fixes | Cross-platform | 6 | 3+ | Mar 2026 | Complete
Cross-Platform User Management | Cross-platform | 6 | 3+ | Mar 2026 | Complete
Multi-User Install (ossh) | Cross-platform | 13 | 4+ | Mar–Apr 2026 | Complete
SSH / ControlMaster | Cross-platform | 5 | 2+ | Feb–Mar 2026 | Complete
Shared SSH Config + Deploy Key | Cross-platform | 9 | 3+ | Apr 2026 | Complete
Docker Socket Access | Cross-platform | 10 | 3+ | Apr 2026 | Complete
Test Suite Framework | Cross-platform | 7 | 3+ | Feb–Mar 2026 | Complete
State Machine Fixes | Cross-platform | 4 | 4+ | Mar 2026 | Complete
Branching Strategy + Promote | Cross-platform | 30+ | 5+ | Mar 2026 | Complete
TOTAL |  | 250+ | 25+

## Work Areas Detail
Work Areas — Detailed Breakdown
Work Area | Description | What Was Done | Key Commits | Key Files
Package Manager (dnf/yum) | OOSH only supported apt-get and brew; AlmaLinux requires dnf/yum | Added dnf/yum detection to bootstrap (init/oosh), framework core (oo cmd install/update), completion system (c2.install.linux), Python venv setup for tests (otest), and user-facing install hints (claudeFlow). 5 files, +47/-6 lines | d6de39a | init/oosh, oo, ng/c2, otest, claudeFlow
POSIX Compatibility | AlmaLinux minimal install lacks GNU tools; which, moreutils, GNU sed extensions caused failures | Replaced which with command -v in 9 files (fixed 'sudo: command not found' on bootstrap); removed moreutils dependency by replacing errno with Python3 os.strerror(); fixed POSIX BRE regex \? causing 'bad regex' in completion system; set git user identity in test fixtures for containers lacking global git config | 0f23296, dc7e701, 8f6784b, 848c755 | init/oosh, config, debug, loop, ng/c2, state, this, oo
Docker Infrastructure (odocker) | No Docker wrapper existed; platform testing needed container lifecycle management | Built odocker wrapper from scratch: 18 methods including build, run.sshd, reset, rebuild, clone, enter, exec, install (auto-detects OS for Docker CLI), workspace/container/image list, status, disk, prune. ~450 lines, 90+ test assertions, full tab completion, documentation at docs/odocker.md | 68 commits (Feb–Apr) | odocker, test/test.odocker, docs/odocker.md
AlmaLinux Docker Image | No AlmaLinux container image existed for automated testing | Created nakedAlma/9.sshd workspace and Dockerfile: almalinux:9 base + openssh-server + sudo + wget (229 MB). Built matching images for Ubuntu 24.04 (218 MB), Debian 12 (172 MB), Alpine 3.19 (15.7 MB) | 3f59cf8 | workspaces/nakedAlma/9.sshd/Dockerfile
Installation Fixes (ossh install) | ossh install failed on RHEL/AlmaLinux: wrong sudo group, missing TTY, PATH override by secure_path | Fixed wheel vs sudo group detection in user.create; added -tt (force TTY) for sudo password prompts over SSH; solved AlmaLinux secure_path overriding PATH with sudo bash -lc; added glob guards for mv *.public_key; state machine guards for missing dirs; suppressed bootstrap 'no OS found' noise | c243b05, 16ec820, 7362817, 9c76f42 | ossh, user, oo, init/oosh
User Management (RHEL) | RHEL/AlmaLinux auto-creates User Private Group matching username, causing useradd to fail | RHEL auto-creates a User Private Group with same name as user; if a 'dev' group already exists, useradd fails. Fixed with -N (skip UPG creation) and -g (use existing group) | 3c65194 | user
Platform Test Infrastructure | No automated way to test OOSH on AlmaLinux or any other platform | Built 3 new methods: os platform.test <platform>, os platform.test.all, os platform.list. Automated flow per platform: odocker reset (fresh container) → SSH key push → ossh install → test.suite core 1 → evaluate results. Added notests parameter for install-only testing. 362/363 assertions pass on AlmaLinux | 5db7742, 61 commits total | os, defaults/platforms.env, test/test.os
Release Pipeline | No gated release process; AlmaLinux needed to be a promotion gate | Created promote script with 15-state PROMOTE state machine: dev→stage gated by core tests, stage→prod gated by platform tests on all 5 must-pass targets. Resumable pipeline (failed promotions resume from failing step). Includes promote.status and promote.report. First release v1.0.0 on 2026-03-11 | 20+ commits (Mar 2026) | promote, test/test.promote, docs/promote.md, docs/branching.md
Portable Shell (sed -i) | GNU sed -i and BSD sed -i '' differ; macOS/AlmaLinux compatibility broken | GNU sed -i (Linux) vs BSD sed -i '' (macOS) differ. Implemented uname -s platform detection wrapper so all in-place edits work on both. Also added dynamic root home detection (/root vs /var/root) and macOS shell detection | eb76df4 | oo, ossh
Login Shell / .bashrc Fixes | OOSH environment failed to load in login shells inside Docker containers on various platforms | Created .bash_profile that sources .bashrc on login shells (SSH, Docker containers). Used ~ instead of $HOME for portability. Set bash as default login shell during remote install. Fixed root login shell on Alpine (ash → bash). Restored root shell setup lost during merge | 3f691ec, 70abd31, 9b396a3, c3ad938, d1abbbf, 737cbcd | ossh, init/oosh
Cross-Platform User Management | user.create failed on Debian (/usr/sbin not in PATH) and Alpine (adduser differences) | Runtime detection of useradd vs adduser (not hardcoded per OS). Added /usr/sbin to PATH for Debian where useradd lives outside default PATH. Handled Alpine's adduser differences and existing group conflicts. usermod compatibility across all platforms | 6b368a4, bcfde06, 91ad7e8, 2b4063f, 075b4a3, ca098aa | user, ossh, oo
Multi-User Install (ossh) | ossh install only supported single-user; CI required root install + second dev user | Extended ossh install for multi-user scenarios: auto-create user if missing, root-first platform test with second dev user, cross-user home access via sudo -u, targetHome for install.user.remote, skip bootstrap if oosh already installed. CI hardening: tolerate connection drops, local sudo for sudoers, fix awk escaping | 13 commits (Mar–Apr) | ossh, os
SSH / ControlMaster | SSH session management caused hangs and stale connections during platform tests | Set OSSH_CONTROL_PATH for sshpass and non-interactive ssh-keygen. Clean stale ControlMaster socket before sshpass connection. Use 'true' command instead of -N -f for ControlMaster. Reopen ControlMaster after install (group membership refresh). Close ControlMaster so dev group changes take effect | 97d8cce, f46df83, 2c70729, 9961051, d65708a | ossh
Shared SSH Config + Deploy Key | Multi-user Docker containers needed shared GitHub SSH access across users | Designed and built shared SSH config for multi-user Docker containers: ossh.config.shared.create at /home/shared/.ssh/config, ossh.config.shared.link per-user, integrated into ossh.install. Copy (not symlink) SSH config per-user for robustness. Deploy key copied per-user with ~/.ssh/2cuGitHub identity | fafbdd2, 59d6341, 1b5c427, 233c62d, ba85e25, 178bb0d, 11cb876, 8537ca9, 4790fae | ossh
Docker Socket Access | Containers (including AlmaLinux) needed Docker-in-Docker for platform testing | Add users to docker group on install for socket access. Auto-detect and fix Docker socket GID mismatch (host vs container). Use sudo -n for non-interactive socket fix. Suppress oosh logging during group setup (logging not yet loaded). Check socket access only before build/rebuild/reset (performance) | 86744e3, 759168f, 420ba44, 3ef277c, dda4742, f6327a7, 9a39a65, 36dda9e, 87184ef, 41d0c0e | odocker
Test Suite Framework | Test suite failed across Docker root, test user, and AlmaLinux environments | Split tests into core (22 files, gates promotion) and extended (27 files) categories. Fixed test.suite all 1 to pass on host, Docker root, and Docker test user. Use /tmp for temp files (permission fix for test users). Use $OOSH_DIR instead of relative paths. Fixed aggregation counters, debug toggle, and completion registration | edbd6be, d956487, 974554a, 55979f2, f692d9c, 67acc90, 541105a | test.suite, otest
State Machine Fixes | Sparse array lookup caused state machine to skip states; found during v1.0.0 AlmaLinux promotion | Fixed sparse array lookup in state machine advancement — states [21]-[26] were unreachable, discovered during v1.0.0 stage→prod promotion. Comprehensive fixes to framework and all consumers. Persist state machine files across users. Set git safe.directory for multi-user installs. Added Darwin support | 162e026, dbd1431, fd4350d, 90cdaa4 | state, oo, user
Branching Strategy + Promote | No formal release pipeline; AlmaLinux needed to be a mandatory gate before production | Defined complete dev→stage→prod branching strategy. Built promote script with 15 state-machine check functions. Stage promotion gated by core tests. Production promotion gated by platform tests on all 5 must-pass targets (including AlmaLinux). Resumable pipeline — failed promotions restart from failing step. Skip parameter for manual override. promote.status and promote.report for visibility | 8e16e6b, e3e09ca, 5db7742, 4f74c87, a52b9c1 + 25 more | promote, docs/branching.md, docs/promote.md

## Platform Matrix
Platform Test Matrix — OOSH v1.0.20
Test Date: |  | 2026-04-13
Release: |  | v1.0.0
Platform | Package Manager | Tier | Image Size | Test Assertions* | Pass Rate | Status
Ubuntu 24.04 | apt-get | must-pass | 218 MB | 362/363 | 100% | Pass
Debian 12 | apt-get | must-pass | 172 MB | 362/363 | 100% | Pass
AlmaLinux 9 | dnf | must-pass | 229 MB | 362/363 | 100% | Pass
Alpine 3.19 | apk | must-pass | 15.7 MB | 362/363 | 100% | Pass
macOS | brew | must-pass | N/A | 362/363 | 100% | Pass
CentOS 7 | yum | best-effort | N/A | N/A | N/A | N/A
Arch Linux | pacman | best-effort | N/A | N/A | N/A | N/A
* 1 intentional meta-test failure on AlmaLinux 9: a test that verifies failure detection itself — expected behaviour, not a regression.
Promotion Gates
Gate |  | Requirement |  |  | Result
dev → testing |  | All core tests pass |  |  | Passed
testing → prod |  | Platform tests pass on all 5 must-pass targets (5/5) |  |  | Passed 5/5